## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3658145 | 68397 | ATM Project | 20 | ATM_1-20 | 292929 | Bug | 93053 | RFT | 64129 | 1.1 | Display error while showing amounts | **1. The function being tested (e.g., Login)** Display graphics **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** Menu items showing amounts to withdraw **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card details 2. Select the transaction type as "Withdraw" 3. Select any of the account type **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** All amounts to be shown in a standard way with '$' followed by the value **5. What was the actual outcome?** The amount "60" is missing the '$' sign **6. What was the log output?** | 1 | Open | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319947 | Rahul Ravi | Jan. 29, 2022 12:20 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:24 | 1 | 0 | Jan. 29, 2022 17:24 Mahdi Jaberzadeh Ansari @Rahul Ravi Let's keep its status new, because we found it in the new version of the app.
3658194 | 68397 | ATM Project | 24 | ATM_1-24 | 292929 | Bug | 93053 | RFT | 64129 | 1.1 | Wrong error message (Invalid account type) | **1. The function being tested (e.g., Login)** Balance inquiry and its output **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquiry 4. Then select the Money Market account 5. Does nothing, check the screen **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Showing a status that indicates "Invalid account type" **5. What was the actual outcome?** ![image][pasted-2022.01.29-16.25.12.png] **6. What was the log output?** > Message: INQUIRY CARD# 1 TRANS# 1 FROM 2 NO TO NO AMOUNT > Response: FAILURE Invalid account type | 1 | Open | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319945 | Shirin | Jan. 29, 2022 16:25 |  | 319945 | Shirin | Jan. 29, 2022 16:25 | 1 | 0
3658080 | 68397 | ATM Project | 1 | ATM_1-1 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Wrong card number in the printer output | **1. The function being tested (e.g., Login)** Balance inquery and its output **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquery 4. Then select the checking acount 5. The card number in the printer is shown as card #2 **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** > Sat Jan 29 09:17:43 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 1 TRANS #1 > INQUIRY FROM: CHKG > > TOTAL BAL: $100.00 > AVAILABLE: $100.00 **5. What was the actual outcome?** > Sat Jan 29 09:17:43 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > INQUIRY FROM: CHKG > > TOTAL BAL: $100.00 > AVAILABLE: $100.00 ![image][pasted-2022.01.29-09.19.12.png] **6. What was the log output?** > Message: INQUIRY CARD# 1 TRANS# 1 FROM 0 NO TO NO AMOUNT > Response: SUCCESS | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 09:27 |  | 319945 | Shirin | Jan. 29, 2022 16:34 | 1 | 0 | Jan. 29, 2022 16:28 Shirin The error still exist in the new version. Here is the printer in version 1.1: > Sat Jan 29 16:26:34 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > **CARD 2 ** TRANS #2 > INQUIRY FROM: CHKG > > TOTAL BAL: $100.00 > AVAILABLE: $100.00
3658088 | 68397 | ATM Project | 2 | ATM_1-2 | 292929 | Bug | 93052 | MFT | 64128 | 1.0 | Wrong amount is shown for Money Market account | **1. The function being tested (e.g., Login)** Balance inquery and its output **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquery 4. Then select the Money Market account (option 2) 5. The account in the printer is shown is the saving account and not the Money Market account **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** > Sat Jan 29 09:17:43 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 1 TRANS #1 > INQUIRY FROM: MMKA > > TOTAL BAL: $5000.00 > AVAILABLE: $5000.00 **5. What was the actual outcome?** > Sat Jan 29 09:43:57 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #2 > INQUIRY FROM: SVGS > > TOTAL BAL: $1000.00 > AVAILABLE: $1000.00 ![image][pasted-2022.01.29-10.04.14.png] **6. What was the log output?** > Message: INQUIRY CARD# 1 TRANS# 2 FROM 1 NO TO NO AMOUNT > Response: SUCCESS > Dispensed: $500.00 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:04 |  | 319945 | Shirin | Jan. 29, 2022 16:29 | 1 | 0
3658089 | 68397 | ATM Project | 3 | ATM_1-3 | 292929 | Bug | 93056 | MFT & RFT | 64128 | 1.0 | Entering an unreadable card number | **1. The function being tested (e.g., Login)** System rejects an unreadable card **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and not servicing a customer **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Select insert card 2. Enter an unreadable card number greater than zero 3. Press enter **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Card is ejected; System displays an error screen; System is ready to start a new session **5. What was the actual outcome?** Input is accepted and system asks for PIN **6. What was the log output?** ![image][pasted-2022.01.29-10.05.58.png] **7. Test case number** 6 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319947 | Rahul Ravi | Jan. 29, 2022 10:05 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:18 | 1 | 0 | Jan. 29, 2022 12:02 Rahul Ravi Error still persists in Version 1.1
3658094 | 68397 | ATM Project | 5 | ATM_1-5 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Strange output on the screen and losing money when user is trying to check the blance of the Money Market account | **1. The function being tested (e.g., Login)** Balance inquery and its output **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquery 4. Then select the Money Market acount 5. Does nothing, check the screen **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Showing a status that is understandable for the user. It does not say what was the error! **5. What was the actual outcome?** In the log section it shows the user despensed $500 and gives the user $500, however, user tried to check the balance. ![image][pasted-2022.01.29-10.17.41.png] **6. What was the log output?** > Message: INQUIRY CARD# 1 TRANS# 4 FROM 1 NO TO NO AMOUNT > Response: SUCCESS > Dispensed: $500.00 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:19 |  | 319945 | Shirin | Jan. 29, 2022 16:36 | 1 | 0 | Jan. 29, 2022 16:21 Shirin Error has been resolved. But another error is shown that will be reported in another ticket. | Jan. 29, 2022 16:36 Shirin If we select the saving account then still we see the "Unknown Error" message on the screen.
3658104 | 68397 | ATM Project | 7 | ATM_1-7 | 292929 | Bug | 93056 | MFT & RFT | 64128 | 1.0 | System performs a legitimate transfer transaction properly | **1. The function being tested (e.g., Login)** System performs a legitimate transfer transaction properly **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is displaying a request for the customer to type a dollar amount **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** Select Transfer, select transfer account from and to, enter dollar amount **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) **5. What was the actual outcome?** System prints the correct balance and the log show correctly but while displaying the message when selecting transfer from account as checking and transfer to account as saving it displays 'SVGS to CHKG' instead of 'CHKG to SVGS' **6. What was the log output? ** Message: TRANSFER CARD# 1 TRANS# 14 FROM 0 TO 1 $4.50 Response: SUCCESS **7. Test case number: 29 ![image][Screen Shot 2022-01-29 at 10.27.28 AM.png] ** | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319853 | Aadharsh Hariharan | Jan. 29, 2022 10:29 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:24 | 1 | 0 | Jan. 29, 2022 14:24 Rahul Ravi Issue still persists in Version 1.1
3658106 | 68397 | ATM Project | 8 | ATM_1-8 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Despensing money during the process of showing the account balance | **1. The function being tested (e.g., Login)** Balance inquery and its output **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquery 4. Then do not select option 1 or 2 5. Press on any key from 3 to 9 or 0 6. The ATM will give you $20 **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Showing a suitable message that the pressed key is invalid **5. What was the actual outcome?** I got $20 ![image][pasted-2022.01.29-10.32.17.png] **6. What was the log output?** > Dispensed: $20.00 | 2 | In Progress | 2 | High | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:32 |  | 319945 | Shirin | Jan. 29, 2022 16:33 | 1 | 0 | Jan. 29, 2022 16:32 Shirin The problem still exist for key #4
3658110 | 68397 | ATM Project | 10 | ATM_1-10 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Strange value being displayed during option selection (outside the ones suggested) | **1. The function being tested (e.g., Login)** Entering an option number that is not present in the menu **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** A menu with options to choose from **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** Enter an option number not present in the display **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Nothing should happen or an error message saying incorrect option selected **5. What was the actual outcome?** The value "$20" is being displayed **6. What was the log output?** Dispensed: $20.00 | 2 | In Progress | 2 | High | 64129 | 1.1 |  |  |  |  | 319947 | Rahul Ravi | Jan. 29, 2022 10:40 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 14:17 | 1 | 0 | Jan. 29, 2022 12:04 Rahul Ravi Problem still exists in Version 1.1
3658122 | 68397 | ATM Project | 13 | ATM_1-13 | 292929 | Bug | 93056 | MFT & RFT | 64128 | 1.0 | Invalid PIN Extension | **1. The function being tested (e.g., Login)** Correct re-entry of PIN is accepted **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** Request to re-enter PIN is being displayed **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** Enter incorrect pin, then enter correct pin. **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Original transaction completes successfully **5. What was the actual outcome?** Asks to enter pin again after entering correct pin **6. What was the log output?** **7. Test case number** 37 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319853 | Aadharsh Hariharan | Jan. 29, 2022 11:21 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:25 | 0 | 0 | Jan. 29, 2022 14:25 Rahul Ravi Issue still persists in Version 1.1
3658123 | 68397 | ATM Project | 14 | ATM_1-14 | 292929 | Bug | 93056 | MFT & RFT | 64128 | 1.0 | Invalid PIN Extension- Correct re-entry of PIN on the second try is accepted | **1. The function being tested (e.g., Login)** Correct re-entry of PIN on the second try is accepted **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** Request to re-enter PIN is being displayed **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** Enter incorrect PIN the first time, then correct PIN the second time **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Original transaction completes successfully **5. What was the actual outcome?** Asks to enter pin again after entering correct pin **6. What was the log output?** **7. Test case number** 39 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319853 | Aadharsh Hariharan | Jan. 29, 2022 11:23 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:26 | 0 | 0 | Jan. 29, 2022 14:26 Rahul Ravi Issue still persists in Version 1.1
3658124 | 68397 | ATM Project | 15 | ATM_1-15 | 292929 | Bug | 93056 | MFT & RFT | 64128 | 1.0 | Invalid PIN Extension-Correct re-entry of PIN on the third try is accepted | 1. The function being tested (e.g., Login) Correct re-entry of PIN on the second try is accepted 2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) Request to re-enter PIN is being displayed 3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) Enter incorrect PIN the first time and second times, then correct PIN the third time 4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) Original transaction completes successfully 5. What was the actual outcome? Asks to enter pin again after entering correct pin 6. What was the log output? 7. Test case number 40 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319853 | Aadharsh Hariharan | Jan. 29, 2022 11:24 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:27 | 0 | 0 | Jan. 29, 2022 14:27 Rahul Ravi Issue still persists in Version 1.1
3658129 | 68397 | ATM Project | 16 | ATM_1-16 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Successful withdrawal after reaching daily limit | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Saving acount 5. Then select $100 as your request 6. Check the success message 7. Press 1 for new request 8. Repeat steps 3 to 5 again 9. Check the error message as "Daily withdrawal limit exceeded" 10. Press 1 for new request 11. Repeat steps 3 to 5 again for Checking account 12. Get the money! **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** It must not allow getting money anymore after reaching the limitation **5. What was the actual outcome?** > Sat Jan 29 11:35:30 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > WITHDRAWAL FROM: SVGS > AMOUNT: $200.00 > TOTAL BAL: $800.00 > AVAILABLE: $800.00 > Sat Jan 29 11:36:28 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #3 > WITHDRAWAL FROM: CHKG > AMOUNT: $40.00 > TOTAL BAL: $60.00 > AVAILABLE: $60.00 > Sat Jan 29 11:36:55 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #4 > WITHDRAWAL FROM: SVGS > AMOUNT: $40.00 > TOTAL BAL: $760.00 > AVAILABLE: $760.00 **6. What was the log output?** > Message: WITHDRAW CARD# 1 TRANS# 1 FROM 1 NO TO $200.00 > Response: SUCCESS > Dispensed: $200.00 > Message: WITHDRAW CARD# 1 TRANS# 2 FROM 1 NO TO $200.00 > Response: **FAILURE Daily withdrawal limit exceeded** > Message: WITHDRAW CARD# 1 TRANS# 3 FROM 0 NO TO $40.00 > Response: SUCCESS > Dispensed: $40.00 > Message: WITHDRAW CARD# 1 TRANS# 4 FROM 1 NO TO $40.00 > Response: SUCCESS > Dispensed: $40.00 | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 11:45 |  | 319945 | Shirin | Jan. 29, 2022 16:50 | 0 | 0 | Jan. 29, 2022 16:50 Shirin Unfortunately, the bug still exist in the new version too. > Sat Jan 29 16:46:06 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #3 > WITHDRAWAL FROM: SVGS > AMOUNT: $200.00 > TOTAL BAL: $800.00 > AVAILABLE: $800.00 > Sat Jan 29 16:46:43 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #5 > WITHDRAWAL FROM: CHKG > AMOUNT: $20.00 > TOTAL BAL: $60.00 > AVAILABLE: $60.00
3658133 | 68397 | ATM Project | 17 | ATM_1-17 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Wrong error message (Invalid account type) | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Money Market acount 5. Then select $200 as your request 6. Check the error message on the screen. **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Getting money as requested **5. What was the actual outcome?** ![image][pasted-2022.01.29-11.51.45.png] **6. What was the log output?** > Message: WITHDRAW CARD# 1 TRANS# 5 FROM 2 NO TO $20.00 > Response: FAILURE Invalid account type | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 11:51 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:11 | 1 | 0 | Jan. 29, 2022 12:16 Mahdi Jaberzadeh Ansari Saw same error when tried to deposit money to the Money Market account. | Jan. 29, 2022 17:11 Mahdi Jaberzadeh Ansari The error still exist in the new version too
3658139 | 68397 | ATM Project | 18 | ATM_1-18 | 292929 | Bug | 93057 | EFT & RFT | 64129 | 1.1 | Wrong total balance after depositing money | **1. The function being tested (e.g., Login)** Money deposit **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to deposit money to his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 2 for the Deposit 4. Then select the Checking acount 5. Then select $5 as your desired amount 6. Inser the envelope 6. Check how much the ATM shows as the available balance **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** I had $100, I expected to see $105, but it reduced $5 first and showed $95 as the initial value and at the end $100 as available. **5. What was the actual outcome?** > Sat Jan 29 11:58:43 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > DEPOSIT TO: CHKG > AMOUNT: $5.00 > TOTAL BAL: $95.00 > AVAILABLE: $100.00 **6. What was the log output?** > Message: INIT_DEP CARD# 1 TRANS# 1 NO FROM TO 0 $5.00 > Response: SUCCESS > Envelope: received > Message: COMP_DEP CARD# 1 TRANS# 1 NO FROM TO 0 $5.00 > Response: SUCCESS | 2 | In Progress | 3 | Normal | 64128 | 1.0 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 12:02 |  | 319945 | Shirin | Jan. 29, 2022 16:57 | 0 | 0 | Jan. 29, 2022 16:57 Shirin It seems the error still exist, however, it seems they have tried to fix it because the values changed: > Sat Jan 29 16:55:06 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > DEPOSIT TO: CHKG > AMOUNT: $5.00 > TOTAL BAL: $104.90 > AVAILABLE: $100.00
3658142 | 68397 | ATM Project | 19 | ATM_1-19 | 292929 | Bug | 93057 | EFT & RFT | 64129 | 1.1 | Wrong available value after depositing money | **1. The function being tested (e.g., Login)** Money deposit **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to deposit money to his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 2 for the Deposit 4. Then select the checking acount 5. Then select $40 as your desired amount 6. Inser the envelope 6. Check how much the ATM shows as the available balance **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** I had $100, I expected to see $140 as available, but at the end $100 as available. Also, log shows 2 times depositing. **5. What was the actual outcome?** > Sat Jan 29 12:09:27 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > DEPOSIT TO: CHKG > AMOUNT: $40.00 > TOTAL BAL: $130.00 > AVAILABLE: $100.00 ![image][pasted-2022.01.29-12.10.47.png] **6. What was the log output?** > Message: INIT_DEP CARD# 1 TRANS# 1 NO FROM TO 0 $40.00 > Response: SUCCESS > Envelope: received > Message: COMP_DEP CARD# 1 TRANS# 1 NO FROM TO 0 $40.00 > Response: SUCCESS | 2 | In Progress | 3 | Normal | 64128 | 1.0 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 12:12 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:11 | 1 | 0 | Jan. 29, 2022 17:10 Mahdi Jaberzadeh Ansari Still the error exist: > Sat Jan 29 17:09:30 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > DEPOSIT TO: CHKG > AMOUNT: $40.00 > TOTAL BAL: $139.90 > AVAILABLE: $100.00
3658188 | 68397 | ATM Project | 22 | ATM_1-22 | 292929 | Bug | 93057 | EFT & RFT | 64128 | 1.0 | Wrong error message (Invalid account type) in money transfer | **1. The function being tested (e.g., Login)** Transfer money **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to transfer money from one of his/her account to another one **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 3 for the Transfer 4. Then select the Checking account as the source 5. Select the Money Market account as the target account 6. Then select $100 as your desired value for transfer 7. Check the screen for the error messages **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** A success message in transferring money to Money Market account **5. What was the actual outcome?** It shows an error message in the screen ![image][pasted-2022.01.29-16.01.22.png] **6. What was the log output?** > Message: TRANSFER CARD# 1 TRANS# 6 FROM 0 TO 1 $99.50 > Response: SUCCESS | 2 | In Progress | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319945 | Shirin | Jan. 29, 2022 16:01 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:16 | 1 | 0 | Jan. 29, 2022 17:16 Mahdi Jaberzadeh Ansari The error exist still in new version.
3658092 | 68397 | ATM Project | 4 | ATM_1-4 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Saving account is missing in the list of the accounts for balance inquery | **1. The function being tested (e.g., Login)** Balance inquery **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to see the balance of his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 4 for the balance inquery 4. Then it shows the list of the accounts **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** The Saving account must be offered as an option **5. What was the actual outcome?** Just can see Checking and Money Market accounts ![image][pasted-2022.01.29-10.10.12.png] **6. What was the log output?** Nothing! | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:11 |  | 319945 | Shirin | Jan. 29, 2022 16:30 | 1 | 0 | Jan. 29, 2022 16:30 Shirin The problem has been resolved and now we have Saving account too.
3658097 | 68397 | ATM Project | 6 | ATM_1-6 | 292929 | Bug | 93052 | MFT | 64128 | 1.0 | Winthdrawal of amount from any account | **1. The function being tested (e.g., Login)** System performs a legitimate withdrawal transaction properly **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is displaying the menu of withdrawal amounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** Choose an amount that the system currently has and which is not greater than the account balance **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) **5. What was the actual outcome?** System takes the next option as the input, the one present after the one selected by the user and tries to dispense that amount (Eg., 1. $20 2. $40 -> When user selects option 1, it tries to dispense $40 instead of $20) **6. What was the log output?** Message: WITHDRAW CARD# 1 TRANS# 1 FROM 0 NO TO $40.00 Response: SUCCESS Dispensed: $40.00 **7. Test case number** 14 ![image][pasted-2022.01.29-10.21.22.png] | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319947 | Rahul Ravi | Jan. 29, 2022 10:21 |  | 319947 | Rahul Ravi | Jan. 29, 2022 14:18 | 1 | 0 | Jan. 29, 2022 12:15 Rahul Ravi Issue resolved in Version 1.1
3658109 | 68397 | ATM Project | 9 | ATM_1-9 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Despending wrong amount (Requested value smaller than the actual blance) | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Checking acount 5. Then select $20 as your request 6. Check how much the ATM is despending! **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Sat Jan 29 10:33:32 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #7 WITHDRAWAL FROM: CHKG AMOUNT: $20.00 TOTAL BAL: $80.00 AVAILABLE: $80.00 **5. What was the actual outcome?** > Sat Jan 29 10:33:32 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #7 > WITHDRAWAL FROM: CHKG > AMOUNT: $40.00 > TOTAL BAL: $60.00 > AVAILABLE: $60.00 ![image][pasted-2022.01.29-10.39.09.png] **6. What was the log output?** > Message: WITHDRAW CARD# 1 TRANS# 7 FROM 0 NO TO $40.00 > Response: SUCCESS > Dispensed: $40.00 | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:39 |  | 319945 | Shirin | Jan. 29, 2022 16:42 | 1 | 0 | Jan. 29, 2022 10:49 Mahdi Jaberzadeh Ansari Saw the same error when pressed the key 6 to 9 or 0 in money withdrawal section, as the possible options was from 1 to 5 for selecting $20, $40, $60, $80, $100 or $200. Therefore, it seems whenever we press a key that is not part of the options we can grab some money. This money dispending does not affect the customer account. | Jan. 29, 2022 16:42 Shirin The problem has been resolved in the new version. Here is the printer output: > Sat Jan 29 16:41:31 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > WITHDRAWAL FROM: CHKG > AMOUNT: $20.00 > TOTAL BAL: $80.00 > AVAILABLE: $80.00
3658112 | 68397 | ATM Project | 11 | ATM_1-11 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Wrong error message: "Insufficient available balance" when enters a bundary value | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Checking acount 5. Then select $100 as your request 6. Check the error message on the screen! **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Despend $100 as the user has suffcient balance **5. What was the actual outcome?** ![image][pasted-2022.01.29-10.43.26.png] **6. What was the log output?** > Message: WITHDRAW CARD# 1 TRANS# 1 FROM 0 NO TO $200.00 > Response: FAILURE Insufficient available balance | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:45 |  | 319945 | Shirin | Jan. 29, 2022 16:40 | 1 | 0 | Jan. 29, 2022 16:40 Shirin The problem has been resolved in the new version.
3658117 | 68397 | ATM Project | 12 | ATM_1-12 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Despending wrong amount (Requested value greater than the actual blance) | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Checking acount 5. Then select $200 as your request 6. Check how much the ATM is despending! **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Showing insufficient blance message **5. What was the actual outcome?** > Sat Jan 29 10:51:49 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #2 > WITHDRAWAL FROM: CHKG > AMOUNT: $20.00 > TOTAL BAL: $80.00 > AVAILABLE: $80.00 **6. What was the log output?** > Message: WITHDRAW CARD# 1 TRANS# 2 FROM 0 NO TO $20.00 > Response: SUCCESS > Dispensed: $20.00 | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 10:56 |  | 319945 | Shirin | Jan. 29, 2022 16:47 | 0 | 0 | Jan. 29, 2022 16:47 Shirin Error has been resolved in the new version: > Sat Jan 29 16:46:06 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #3 > WITHDRAWAL FROM: SVGS > AMOUNT: $200.00 > TOTAL BAL: $800.00 > AVAILABLE: $800.00
3658184 | 68397 | ATM Project | 21 | ATM_1-21 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Wrong values after a successful money transfer | **1. The function being tested (e.g., Login)** Transfer money **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to transfer money from one of his/her account to another one **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 1. Insert card #1 2. Enter the PIN (42) 3. Select option 3 for the Transfer 4. Then select the Checking account as the source 5. Select the saving account as the target account 6. Then select $100 as your desired value for transfer 7. Check the print screen for the final values. **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** Showing $0.0 for the source account and $1100 for the saving account **5. What was the actual outcome?** I showed the balance of the checking account before and after the transfer > Sat Jan 29 15:10:34 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #5 > INQUIRY FROM: CHKG > > TOTAL BAL: $100.00 > AVAILABLE: $100.00 > Sat Jan 29 15:11:23 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #6 > TRANSFER FROM: SVGS TO: CHKG > AMOUNT: $99.50 > TOTAL BAL: $1099.50 > AVAILABLE: $1099.50 > Sat Jan 29 15:12:07 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #7 > INQUIRY FROM: CHKG > > TOTAL BAL: $0.50 > AVAILABLE: $0.50 **6. What was the log output?** > Message: TRANSFER CARD# 1 TRANS# 6 FROM 0 TO 1 $99.50 > Response: SUCCESS | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319945 | Shirin | Jan. 29, 2022 15:37 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:19 | 0 | 0 | Jan. 29, 2022 15:41 Shirin Please notice that the wrong value exist in both the source and the target account | Jan. 29, 2022 17:19 Mahdi Jaberzadeh Ansari The error has been resolved: > Sat Jan 29 17:18:03 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > TRANSFER FROM: SVGS TO: CHKG > AMOUNT: $100.00 > TOTAL BAL: $1100.00 > AVAILABLE: $1100.00 > Sat Jan 29 17:18:22 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #2 > INQUIRY FROM: CHKG > > TOTAL BAL: $0.00 > AVAILABLE: $0.00
3658191 | 68397 | ATM Project | 23 | ATM_1-23 | 292929 | Bug | 93051 | EFT | 64128 | 1.0 | Keys does not work after "Insufficient cash available" error | **1. The function being tested (e.g., Login)** Money withdrawal **2. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer)** System is on and customer tries to withdraw money from his/her accounts **3. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN)** 0. Start the system with only 1 bill -> The ATM has only $20 1. Insert card #1 2. Enter the PIN (42) 3. Select option 1 for the Withdrawal 4. Then select the Checking acount 5. Then select $40 as your request 6. It will show an error message like the following picture 7. Try to select $20, but the key does not work! **4. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu)** When select the lower amount that the system has, it returns the value **5. What was the actual outcome?** ![image][pasted-2022.01.29-16.12.27.png] **6. What was the log output?** Nothing! | 3 | Resolved | 3 | Normal | 64129 | 1.1 |  |  |  |  | 319945 | Shirin | Jan. 29, 2022 16:12 |  | 319946 | Mahdi Jaberzadeh Ansari | Jan. 29, 2022 17:14 | 1 | 0 | Jan. 29, 2022 17:14 Mahdi Jaberzadeh Ansari The problem has been resolved: > Sat Jan 29 17:13:54 MST 2022 > First National Bank of Podunk > ATM #42 Gordon College > CARD 2 TRANS #1 > WITHDRAWAL FROM: CHKG > AMOUNT: $20.00 > TOTAL BAL: $80.00 > AVAILABLE: $80.00